## How to Use
HOW TO USE: INSTRUMENT CABLE SCHEDULE
Colour legend
Yellow cells: type your data here.
Grey cells: formulas. They calculate automatically; do not overwrite them.
Steps
1. Give every cable a unique number that matches the cable tag at both ends.
2. Fill From and To with the instrument, junction box or panel tag.
3. Specify the cable type, pairs or cores, size and screen so procurement can order correctly.
4. Enter the estimated route length; after pulling, update with the actual length.
5. Use Status to track installation progress and the totals to order cable with wastage.
What the formulas do
• Total length = SUM of lengths.
• Order quantity = ROUNDUP(total × (1 + wastage % ÷ 100)).
• Installed and pending counts use the Status column.
Sheets: "Template" is blank and ready to use. "Example" shows a completed form so you can see the expected format.
More free templates, calculators and tools: https://instrumentationblog.in/downloads/templates/

## Template
INSTRUMENT CABLE SCHEDULE
Company: Your Company Name / Logo | [5 empty] | Doc no: Rev:
Yellow cells: enter data. Grey cells: calculated automatically. Free template from instrumentationblog.in
Project
Project | [5 empty] | Area
Wastage allowance (%) | [5 empty] | Date
Cable schedule
Cable number | From | To | Cable type | Pairs / cores | Size (mm²) | Screen | Length (m) | Gland size | Route / tray | Status | Remarks
Total length (m) | [9 empty] | 0
Total to order with wastage (m) | [9 empty] | 0
Cables installed (Closed) | [9 empty] | 0
Cables pending (Open) | [9 empty] | 0
Prepared by |  |  |  | Checked by |  |  |  | Approved by
Name: |  |  |  | Name: |  |  |  | Name:
Signature: |  |  |  | Signature: |  |  |  | Signature:
Date: |  |  |  | Date: |  |  |  | Date:

## Example
INSTRUMENT CABLE SCHEDULE
Company: ABC Process Industries Ltd | [5 empty] | Doc no: CS INST 001 Rev: 0
Yellow cells: enter data. Grey cells: calculated automatically. Free template from instrumentationblog.in
Project
Project |  |  | Boiler 3 upgrade |  |  | Area |  |  | Utilities, unit 100
Wastage allowance (%) |  |  | 10 |  |  | Date |  |  | 2026-10-12
Cable schedule
Cable number | From | To | Cable type | Pairs / cores | Size (mm²) | Screen | Length (m) | Gland size | Route / tray | Status | Remarks
IC 1101 | PT 1101 | JB 11 | Single pair, overall screened, armoured | 1P | 1.5 | Overall | 35 | M20 Ex d | T 11 A | Closed
IC 2101 | TT 2101 | JB 11 | Single pair, overall screened, armoured | 1P | 1.5 | Overall | 48 | M20 Ex d | T 11 B | Closed
IC 3101 | FT 3101 | JB 12 | Single pair, overall screened, armoured | 1P | 1.5 | Overall | 22 | M20 Ex d | T 12 A | Open
MP 11 01 | JB 11 | Marshalling MC 1 | 12 pair, individual and overall screened, armoured | 12P | 1 | Individual + overall | 180 | M40 Ex d | Main rack R1 | Closed
MP 12 01 | JB 12 | Marshalling MC 1 | 12 pair, individual and overall screened, armoured | 12P | 1 | Individual + overall | 210 | M40 Ex d | Main rack R1 | Open
PC 4101 | XV 4101 SOV | JB 41 | 3 core, armoured | 3C | 1.5 | None | 18 | M20 Ex d | T 41 A | Open
Total length (m) | [9 empty] | 513
Total to order with wastage (m) | [9 empty] | 565
Cables installed (Closed) | [9 empty] | 3
Cables pending (Open) | [9 empty] | 3
Prepared by |  |  |  | Checked by |  |  |  | Approved by
Name: |  |  |  | Name: |  |  |  | Name:
Signature: |  |  |  | Signature: |  |  |  | Signature:
Date: |  |  |  | Date: |  |  |  | Date: