## How to Use
HOW TO USE: INSTRUMENT COMMISSIONING PROGRESS TRACKER
Colour legend
Yellow cells: type your data here.
Grey cells: formulas. They calculate automatically; do not overwrite them.
Steps
1. List systems and total loops from the instrument index.
2. Update counts for each stage weekly.
3. Percentages calculate automatically.
4. Use remarks for blockers.
5. Share the summary in progress meetings.
What the formulas do
• Stage % = stage count ÷ total loops.
• Overall % = (installed + calibrated + cold loop + hot loop) ÷ (4 × total).
Sheets: "Template" is blank and ready to use. "Example" shows a completed form so you can see the expected format.
More free templates, calculators and tools: https://instrumentationblog.in/downloads/templates/

## Template
INSTRUMENT COMMISSIONING PROGRESS TRACKER
Company: Your Company Name / Logo | [5 empty] | Doc no: Rev:
Yellow cells: enter data. Grey cells: calculated automatically. Free template from instrumentationblog.in
Project
Project | [5 empty] | Status date
Commissioning lead | [5 empty] | Target handover
Progress by system
System | Description | Total loops | Installed | Calibrated | Cold loop | Hot loop | Installed % | Cold loop % | Hot loop % | Overall % | Remarks
Total loops | [9 empty] | 0
Cold loop checked | [9 empty] | 0
Hot loop checked | [9 empty] | 0
Project overall %
Overall % gives equal weight to the four stages; change the weighting if your project uses different milestones.
Commissioning lead | [5 empty] | Project manager
Name: | [5 empty] | Name:
Signature: | [5 empty] | Signature:
Date: | [5 empty] | Date:

## Example
INSTRUMENT COMMISSIONING PROGRESS TRACKER
Company: ABC Process Industries Ltd | [5 empty] | Doc no: COMM TRK 001 Rev: 0
Yellow cells: enter data. Grey cells: calculated automatically. Free template from instrumentationblog.in
Project
Project |  |  | Boiler 3 upgrade |  |  | Status date |  |  | 2026-10-25
Commissioning lead |  |  | Instrument lead |  |  | Target handover |  |  | 2026-12-15
Progress by system
System | Description | Total loops | Installed | Calibrated | Cold loop | Hot loop | Installed % | Cold loop % | Hot loop % | Overall % | Remarks
SYS 100 | Feed water | 42 | 42 | 40 | 38 | 20 | 100% | 90.48% | 47.62% | 83.33%
SYS 200 | Steam and drum | 55 | 50 | 44 | 30 | 0 | 90.91% | 54.55% | 0% | 56.36%
SYS 300 | Fuel gas | 36 | 36 | 36 | 36 | 36 | 100% | 100% | 100% | 100% | Ready for handover
SYS 400 | Flue gas and CEMS | 18 | 10 | 4 | 0 | 0 | 55.56% | 0% | 0% | 19.44% | Analysers delayed
Total loops | [9 empty] | 151
Cold loop checked | [9 empty] | 104
Hot loop checked | [9 empty] | 56
Project overall % | [9 empty] | 69.87%
Overall % gives equal weight to the four stages; change the weighting if your project uses different milestones.
Commissioning lead | [5 empty] | Project manager
Name: | [5 empty] | Name:
Signature: | [5 empty] | Signature:
Date: | [5 empty] | Date: