## How to Use
HOW TO USE: INSTRUMENT BREAKDOWN MAINTENANCE REPORT
Colour legend
Yellow cells: type your data here.
Grey cells: formulas. They calculate automatically; do not overwrite them.
Steps
1. Enter the tag, start time and who reported the fault as soon as the complaint is received.
2. Record each action as it happens with the time, person and hours.
3. When the instrument is back in service, enter the restored time; downtime is calculated.
4. Write the root cause, not just the symptom, and choose a cause category for later analysis.
5. Record spares used and add a recommendation to prevent repeat failures.
What the formulas do
• Downtime (hours) = (restored − breakdown start) × 24.
• Total man hours = SUM of action hours.
Sheets: "Template" is blank and ready to use. "Example" shows a completed form so you can see the expected format.
More free templates, calculators and tools: https://instrumentationblog.in/downloads/templates/

## Template
INSTRUMENT BREAKDOWN MAINTENANCE REPORT
Company: Your Company Name / Logo |  |  | Doc no: Rev:
Yellow cells: enter data. Grey cells: calculated automatically. Free template from instrumentationblog.in
Breakdown details
Tag number |  |  | Instrument
Area |  |  | Work order
Reported by |  |  | Criticality
Breakdown start |  |  | Restored
Downtime (hours) |  |  | Production affected?
Fault and root cause
Symptom |  |  | Diagnostic message
Root cause |  |  | Cause category
Actions taken
Date and time | Action |  |  |  | By | Man hours
Total man hours |  |  |  |  | 0
Spares used
Part |  | Part number |  | Qty | Remarks
Prevention
Recommendation |  |  | PM updated?
Attended by | Shift in charge |  | Maintenance head
Name: | Name: |  | Name:
Signature: | Signature: |  | Signature:
Date: | Date: |  | Date:

## Example
INSTRUMENT BREAKDOWN MAINTENANCE REPORT
Company: ABC Process Industries Ltd |  |  | Doc no: BD 26 0118 Rev: 0
Yellow cells: enter data. Grey cells: calculated automatically. Free template from instrumentationblog.in
Breakdown details
Tag number | FT 3101 |  | Instrument |  | Magnetic flowmeter
Area | Column area |  | Work order |  | BD 26 0118
Reported by | Shift operator |  | Criticality |  | High
Breakdown start | 2026-10-11 22:40 |  | Restored |  | 2026-10-12 02:10
Downtime (hours) | 3.5 |  | Production affected? |  | Yes, feed on manual 3.5 h
Fault and root cause
Symptom | Flow reading jumping 0 to 120 m³/h |  | Diagnostic message |  | Empty pipe detected
Root cause | Electrode coating from process scaling |  | Cause category |  | Process
Actions taken
Date and time | Action |  |  |  | By | Man hours
2026-10-11 22:55 | Checked display and diagnostics; empty pipe alarm active although line full |  |  |  | Tech A | 0.5
2026-10-11 23:30 | Feed control put on manual with operations; line isolated and drained |  |  |  | Tech A | 1
2026-10-12 00:30 | Removed sensor, cleaned electrodes, checked electrode resistance |  |  |  | Tech A, Tech B | 3
2026-10-12 01:45 | Reinstalled, empty pipe adjustment done, flow verified against pump curve |  |  |  | Tech B | 1
Total man hours |  |  |  |  | 5.5
Spares used
Part |  | Part number |  | Qty | Remarks
Flange gaskets, PTFE, 3" |  | Store 41 0332 |  | 2
Prevention
Recommendation | Add electrode cleaning to monthly PM; evaluate sensor with cleaning function |  | PM updated? |  | Yes
Attended by | Shift in charge |  | Maintenance head
Name: | Name: |  | Name:
Signature: | Signature: |  | Signature:
Date: | Date: |  | Date: