## How to Use
HOW TO USE: MANAGEMENT OF CHANGE (MOC) FORM
Colour legend
Yellow cells: type your data here.
Grey cells: formulas. They calculate automatically; do not overwrite them.
Steps
1. Describe the change, the reason and the tags affected; choose the type and whether it is temporary.
2. Rate severity and likelihood from 1 to 5; the risk score and level are calculated.
3. Mark each review item OK when done, Not OK if still required, or NA.
4. List the implementation and close out actions with owners and due dates.
5. The MOC status stays Open until every action is closed; also clear every Not OK review item before close out.
What the formulas do
• Risk score = severity × likelihood.
• Risk level: HIGH 15 and above, MEDIUM 8 to 14, LOW below 8 (adjust to your risk matrix).
• MOC status = Open while any action is Open; close review items before closing the MOC.
Sheets: "Template" is blank and ready to use. "Example" shows a completed form so you can see the expected format.
More free templates, calculators and tools: https://instrumentationblog.in/downloads/templates/

## Template
MANAGEMENT OF CHANGE (MOC) FORM
Company: Your Company Name / Logo |  |  | Doc no: Rev:
Yellow cells: enter data. Grey cells: calculated automatically. Free template from instrumentationblog.in
Change request
MOC number |  |  | Date raised
Raised by |  |  | Area / unit
Type of change |  |  | Duration
Tags affected |  |  | Temporary until
Description and risk
Proposed change |  |  | Reason
Severity (1 to 5) |  |  | Likelihood (1 to 5)
Risk score |  |  | Risk level
Reviews and documents
No | Check item |  |  | Status | Remarks
1 | P&IDs and loop drawings updated
2 | Instrument index and data sheets updated
3 | Alarm and trip list updated
4 | DCS / PLC / SIS program backed up before and after change
5 | Hazard review (HAZOP or what if) completed where required
6 | SIL calculation reviewed if a SIF is affected
7 | Operating procedures updated and operators trained
8 | Pre start up safety review completed
9 | Spare parts and maintenance plan updated
Open review items |  |  |  |  | 0
Actions
No | Action |  | Owner | Due | Status | Remarks
1
2
3
4
5
6
7
8
Open actions |  |  |  |  | 0
MOC status
Originator |  | Area owner | MOC coordinator
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## Example
MANAGEMENT OF CHANGE (MOC) FORM
Company: ABC Process Industries Ltd |  |  | Doc no: MOC 26 014 Rev: 0
Yellow cells: enter data. Grey cells: calculated automatically. Free template from instrumentationblog.in
Change request
MOC number |  | MOC 26 014 | Date raised |  | 2026-10-14
Raised by |  | Instrument engineer | Area / unit |  | Boiler 3
Type of change |  | Set point change | Duration |  | Permanent
Tags affected |  | PT 1101 A/B/C | Temporary until
Description and risk
Proposed change |  | Raise steam header HH trip from 14.5 to 15.0 bar g | Reason |  | New relief valve set at 16.5 bar g; fewer spurious trips
Severity (1 to 5) |  | 4 | Likelihood (1 to 5) |  | 2
Risk score |  | 8 | Risk level |  | MEDIUM
Reviews and documents
No | Check item |  |  | Status | Remarks
1 | P&IDs and loop drawings updated |  |  | OK
2 | Instrument index and data sheets updated |  |  | OK
3 | Alarm and trip list updated |  |  | OK
4 | DCS / PLC / SIS program backed up before and after change |  |  | OK
5 | Hazard review (HAZOP or what if) completed where required |  |  | OK | What if review held
6 | SIL calculation reviewed if a SIF is affected |  |  | OK
7 | Operating procedures updated and operators trained |  |  | Not OK | Operator briefing planned
8 | Pre start up safety review completed |  |  | NA
9 | Spare parts and maintenance plan updated |  |  | NA
Open review items |  |  |  |  | 1
Actions
No | Action |  | Owner | Due | Status | Remarks
1 | Change SIS set points and update C&E |  | C&I | 2026-10-20 | Closed
2 | Update alarm and trip list |  | C&I | 2026-10-20 | Closed
3 | Brief all shifts on new trip value |  | Operations | 2026-10-25 | Open
4
5
6
7
8
Open actions |  |  |  |  | 1
MOC status |  |  |  |  | Open
Originator |  | Area owner | MOC coordinator
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date: