## How to Use
HOW TO USE: COMMISSIONING PUNCH LIST
Colour legend
Yellow cells: type your data here.
Grey cells: formulas. They calculate automatically; do not overwrite them.
Steps
1. Give every defect a unique punch number and a clear description that anyone can act on.
2. Set the category: A must be closed before start up, B before handover, C may stay open after handover.
3. Assign one responsible party and a target date.
4. When an item is fixed and verified, set Status to Closed and enter the closed date.
5. Review the open counts at every commissioning meeting.
What the formulas do
• Days open = (closed date or today) − raised date.
• Open item counts by category use COUNTIFS on Category and Status.
Sheets: "Template" is blank and ready to use. "Example" shows a completed form so you can see the expected format.
More free templates, calculators and tools: https://instrumentationblog.in/downloads/templates/

## Template
COMMISSIONING PUNCH LIST
Company: Your Company Name / Logo | [5 empty] | Doc no: Rev:
Yellow cells: enter data. Grey cells: calculated automatically. Free template from instrumentationblog.in
Project
Project / system | [5 empty] | Area
Last updated | [5 empty] | Punch list owner
Punch items (A: must close before start up, B: before handover, C: can remain after handover)
Sr | Punch no | Tag / area | Description | Category | Raised by | Raised on | Responsible | Target date | Status | Closed on | Days open | Remarks
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Open category A | [10 empty] | 0
Open category B | [10 empty] | 0
Open category C | [10 empty] | 0
Closed | [10 empty] | 0
Contractor | [5 empty] | Client
Name: | [5 empty] | Name:
Signature: | [5 empty] | Signature:
Date: | [5 empty] | Date:
Formulas:
Days open = IF([Raised on]="","",IF([Closed on]="",TODAY(),[Closed on])-[Raised on])

## Example
COMMISSIONING PUNCH LIST
Company: ABC Process Industries Ltd | [5 empty] | Doc no: PL U3 01 Rev: 0
Yellow cells: enter data. Grey cells: calculated automatically. Free template from instrumentationblog.in
Project
Project / system |  |  | Boiler 3 control system |  |  | Area |  |  | Utilities block
Last updated |  |  | 2026-10-12 |  |  | Punch list owner |  |  | Commissioning lead
Punch items (A: must close before start up, B: before handover, C: can remain after handover)
Sr | Punch no | Tag / area | Description | Category | Raised by | Raised on | Responsible | Target date | Status | Closed on | Days open | Remarks
1 | P 001 | PDT 3105 | M20 gland on M25 entry, replace with M25 Ex d gland | A | QC | 2026-09-28 | Contractor | 2026-10-05 | Closed | 2026-10-03 | 5
2 | P 002 | CP 03 | AI 02 CH 7 to 12: no open circuit alarm | A | Client | 2026-10-01 | Vendor | 2026-10-15 | Open |  | 12
3 | P 003 | JB 11 | Spare cores not ferruled | B | QC | 2026-10-02 | Contractor | 2026-10-20 | Open |  | 11
4 | P 004 | FV 3101 | Valve tag plate missing | C | Operations | 2026-10-05 | Contractor | 2026-10-30 | Open |  | 8
5 | P 005 | HMI 2 | Historian tags not updating | A | Client | 2026-10-08 | IT / Vendor | 2026-10-14 | Open |  | 5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Open category A | [10 empty] | 2
Open category B | [10 empty] | 1
Open category C | [10 empty] | 1
Closed | [10 empty] | 1
Contractor | [5 empty] | Client
Name: | [5 empty] | Name:
Signature: | [5 empty] | Signature:
Date: | [5 empty] | Date:
Formulas:
Days open = IF([Area]="","",IF([Closed on]="",TODAY(),[Closed on])-[Area])