## How to Use
HOW TO USE: VENDOR DOCUMENT REGISTER
Colour legend
Yellow cells: type your data here.
Grey cells: formulas. They calculate automatically; do not overwrite them.
Steps
1. Set the review period agreed in the PO.
2. Log each document when received, with revision.
3. Enter the review code and return date when the review is sent back.
4. Watch OVERDUE items in progress meetings.
5. Resubmissions get a new row with the new revision.
What the formulas do
• Return due = received + review period.
• Status: Returned, OVERDUE if past due, otherwise In review.
Sheets: "Template" is blank and ready to use. "Example" shows a completed form so you can see the expected format.
More free templates, calculators and tools: https://instrumentationblog.in/downloads/templates/

## Template
VENDOR DOCUMENT REGISTER
Company: Your Company Name / Logo | [5 empty] | Doc no: Rev:
Yellow cells: enter data. Grey cells: calculated automatically. Free template from instrumentationblog.in
Register
Project | [5 empty] | Review period (days)
Document controller | [5 empty] | Register date
Documents
No | Document no | Title | PO / vendor | Type | Rev | Received | Review code | Return due | Returned | Status | Remarks
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Documents | [9 empty] | 0
In review | [9 empty] | 0
Overdue | [9 empty] | 0
Rejected (code 3) | [9 empty] | 0
Document controller | [5 empty] | Lead engineer
Name: | [5 empty] | Name:
Signature: | [5 empty] | Signature:
Date: | [5 empty] | Date:
Formulas:
Status = IF([Received]="","",IF([Returned]<>"","Returned",IF(TODAY()>[Return due],"OVERDUE","In review")))

## Example
VENDOR DOCUMENT REGISTER
Company: ABC Process Industries Ltd | [5 empty] | Doc no: VDR 001 Rev: 0
Yellow cells: enter data. Grey cells: calculated automatically. Free template from instrumentationblog.in
Register
Project |  |  | Boiler 3 upgrade |  |  | Review period (days) |  |  | 10
Document controller |  |  | DC team |  |  | Register date |  |  | 2026-10-25
Documents
No | Document no | Title | PO / vendor | Type | Rev | Received | Review code | Return due | Returned | Status | Remarks
1 | V 101 DS 01 | Pressure transmitter datasheets | PO 4501 | Datasheet | B | 2026-10-04 | 2 Approved with comments | 2026-10-14 | 2026-10-12 | Returned
2 | V 102 GA 03 | Control valve GA drawings | PO 4502 | GA drawing | A | 2026-10-09 |  | 2026-10-19 |  | OVERDUE
3 | V 103 CAL 01 | Orifice sizing calculations | PO 4503 | Calculation | A | 2026-10-20 |  | 2026-10-30 |  | In review
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Documents | [9 empty] | 3
In review | [9 empty] | 1
Overdue | [9 empty] | 1
Rejected (code 3) | [9 empty] | 0
Document controller | [5 empty] | Lead engineer
Name: | [5 empty] | Name:
Signature: | [5 empty] | Signature:
Date: | [5 empty] | Date:
Formulas:
Return due = IF([Review period (days)]="","",[Review period (days)]+J6)
Status = IF([Review period (days)]="","",IF([Returned]<>"","Returned",IF(TODAY()>[Return due],"OVERDUE","In review")))